## Blank
Status | Action Item Name | Description | Priority | Effort | Owner | Due Date | Notes

## July 2023
Status | Action Item Name | Description | Priority | Effort | Owner | Due Date | Notes
In Progress | DRAFT_Documentation_Plan | This document lays out the foundation for the Documentation Project. It includes vision, resources, and process to complete the revamp. | Medium | 3 | Dany Garcia | TBD
Complete | ‎ Annual General Role-Based Privacy Training |  | High | 2 |  | 2023-07-31
Complete | ‎ Are You Traveling Soon? ‎ |  | High | 2 |  | 2023-07-31
Complete | Clean Desk Policy With Quiz |  | High | 2 |  | 2023-07-31
Complete | 2022 Kevin Mitnick Security Awareness Training |  | High | 3 |  | 2023-07-31
Complete | Onboarding documentation and Review | This meeting is to review the email, communications and documents used in onboarding new employees, contractors, interns, etc. to CFPB. | Medium | 3 |  | 2023-07-24
Complete | Rules of Behavior Form |  | Low | 1 |  | 2023-07-31
Complete | Submit ticket for access | Need access to SharePoint folders and documents | Medium | 2 |  | 2023-07-31
Complete | ServiceNow ticket submitted for software | Work requires a file compression software | Low | 1 |  | 2023-07-24
Complete | Meeting with Kipp White | Discuss access to Donna Harradine's OneDrive | Medium | 3 |  | 2023-07-21
Complete | New Hire Orientation |  | Low | 2 |  | 2023-07-21
Backlog | Review New Hire Orientation Documents |  | Low | 2 |  | TBD
Complete | RITM0089568 Ticket created |  | Low | 1 |  | 2023-07-17
In Progress | Review Donna's Documents email | Email forwarded by M. Kern with notes from Donna. | Low | 1 |  | TBD
Backlog | OHC's notification for your review and recommend updates |  | Low | 1 |  | TBD
Initiated | How To Link SharePoint to Outlook |  | Low | 1 |  | TBD
In Progress | Training Request Form | A form used when a specific training is being requested. | Low | 1 |  | 2023-07-28
Initiated | Approval Needed: Advisory Request | Email from Cathy - Dany is reviewing the processes so hopefully once the team receives these they know how to process? Also, how does an Advisory get placed on the CFPB Portal ? Do we have standards that we use since I don’t think we post every item Perhaps just send or point to the documented Advisory process and Dany can review. | Low | 2 |  | TBD
Complete | SMO All Hands Meeting | Meet and Greet, discuss expectations, address questions | High | 2 |  | 2023-07-03
Complete | CSA Tuesday Weekly Meetings | Discuss documentation efforts | Low | 2 |  | Recurring
Complete | Training Document Discussion | Met with Nelly C. to disucss the painpoints in Training | Low | 2 |  | 2023-07-19
Complete | Service Desk Meeting | Met with SD Management to discuss SD needs | Low | 2 |  | 2023-07-06
Complete | YubiKey Training | Was trained on the YubiKey and Windows Hello process | Medium | 2 |  | 2023-07-19
Complete | Service Desk ORR | Discuss ways we can improve our current process for bring new/updated solutions. | Low | 2 |  | 2023-07-24
Complete | Onboarding documentation review and updates | This meeting is to review the email, communications and documents used in onboarding new employees, contractors, interns to CFPB. | Low | 2 |  | 2023-07-26
Complete | Onboarding discussion | Issues/ pain points from Kipp and Brandon with Cathy | Low | 1 |  | 2023-07-28
Complete | eStorefront Reporting Review | Discuss Possible Transition of Tasks | Low | 1 |  | 2023-07-28
Complete | Met with Joe Gilchrist | YubiKey Instuctions discussion | Medium | 3 |  | 2023-07-26
Complete | Training and Documentation methods document |  | Low |  |  | 2023-07-28
Complete | CFPB Work Instruction template |  | Low | 1 |  | 2023-07-31
In Progress | Windows Hello Enrollment Guide update |  | Medium | 3 |  | TBD | Need to go through the steps with onboarding users.
In Progress | YubiKey Seup Guide |  | Medium | 3 |  | TBD | Need to go through the steps with onboarding users.
Initiated | Windows Hello/YubiKey presentations |  | Low | 3 |  | TBD
Initiated | Windows Hello Troubleshooting Guide |  | Medium | 3 |  | TBD | Need to utilize ServiceDesk staff

## August 2023
Status | Action Item Name | Description | Priority | Effort | Owner | Due Date | Notes
Complete | Create Task Board in ServiceNow | Allows me to track and focus on projects based on need, progression, and resources. | Low | 2 |  | N/A
Complete | Update CFPB Work Instruction form | Updated the color scheme to match CFPB | Low | 1
Complete | Statement of Work (SOP) template | Helps to identify responsible parties for projects | Low | 2
Complete | Meeting Notes Template |  | Low | 1
Complete | KnowledgeBase Backlog spreadsheet | Helps identify the backlog items and timeline details | High | 2
In Progress | Email from M. Kern to retire specific documents |  | Medium | 3 |  |  | This will be done once I have completed the training and impletented notes.
Complete | Updating Handheld Computing Devices |  | Medium | 3
In Progress | Data Loss Prevention (DLP) Technical Review/Demo | To establish a Data Loss Prevention (DLP) minimal viable product for Exchange and Teams chat/messaging applications using Microsoft Purview. | High | 3
In Progress | Xerox VersaLink C505 Quick Reference Guide |  | High | 3
In Progress | Configuring a Print Queue and Network Printer_August 2023 |  | High | 3
In Progress | IO_SD_Xerox_Printer_Management_WI |  | High | 3
Complete | QRG Vulnerability Response for Remediation Owners | Changes to original article | Low | 2
In Progress | QRG Vulnerability Response for Approvers | Changes to original article | Low | 2
In Progress | Establishing KB Wiki article standards | This will help by having templates ready for articles to make site appear more uniform and improve the process flow | Low | 2
In Progress | CFPB ENF Trial Device Setup Instructions |  | Low | 2
Complete | Chaired 2 meetings to discuss documentation work progress |  | Medium | 2
Complete | Attended 6 meetings to lend my expertise on the documentation process |  | Medium | 2
In Progress | YubiKey Documentation verification |  | High | 3
In Progress | Windows Hello User Guide verification |  | High | 3
In Progress | CFPB ENF Trial Device Setup Instructions |  | Medium | 2